## Instructions
Pre-Production Release Evidence Tracker – Lloyds Banking Group
Multi-release tracker for CI/CD pipeline governance and production deployment approval
PURPOSE
Use this workbook to track pre-production validation evidence for every release moving through the CI/CD pipeline. One row = one release. The Lead Solution Architect (or delegated approver) should only approve a release for Production once all required evidence is captured and the Overall RAG Status is Green.
HOW TO USE
1. Add a new row to the 'Release Tracker' sheet for each release as it enters the pipeline.
2. Update the status columns as each stage of pre-prod validation is completed (functional testing, security scan, performance testing, UAT sign-off, rollback test, post-deployment plan).
3. Link to the underlying evidence (test reports, scan results, sign-off emails, the companion Word evidence form, etc.) in the 'Evidence Repository Link' column.
4. The 'Overall RAG Status' and 'Approval Status' columns use dropdown lists — select the appropriate value; colour formatting is applied automatically.
5. The Approver records their decision, comments, and approval date directly in the tracker — this becomes the audit trail.
COMPANION TEMPLATE
For a detailed, per-release evidence pack (with full testing tables, rollback plan, and sign-off form), use the companion Word document: 'Release_PreProd_Evidence_Template.docx'. Attach the completed Word form as evidence and link it in this tracker.
COLUMN GUIDE
Column
• Release ID — Unique identifier for the release (e.g. REL-2026-0417).
• Application / Service — Name of the application, service, or system being deployed.
• Release Version / Build — Version number or build identifier from the CI/CD pipeline.
• Change Request (CR) # — Reference number from the ITSM / change management tool.
• Release Type — Standard, Emergency, or Major.
• Business Criticality — Low, Medium, High, or Critical.
• Release Manager — Person coordinating the release.
• Lead Solution Architect (Approver) — Person accountable for reviewing evidence and approving production deployment.
• Target Prod Deployment Date — Planned date/time of production go-live.
• Pipeline Build / Run # — CI/CD pipeline run identifier or link.
• Pre-Prod Deployment Date — Date the build was deployed to the pre-production environment.
• Environment Parity Confirmed — Yes/No/Partial — confirms pre-prod configuration matches production.
• Functional Testing Status — Not Started / In Progress / Pass / Fail / Conditional Pass.
• Functional Test Pass % — Percentage of functional/regression test cases passed.
• Security Scan Status — Not Started / In Progress / Pass / Fail / Conditional Pass.
• Security – Critical/High Open — Count of open Critical/High vulnerabilities from SAST/DAST scans.
• Performance Test Status — Not Started / In Progress / Pass / Fail / Conditional Pass.
• UAT Sign-off Status — Not Started / In Progress / Pass / Fail / Conditional Pass.
• Rollback Plan Tested — Yes/No/Partial — confirms rollback was validated in pre-prod.
• Post-Deployment Validation Plan Ready — Yes/No/Partial — confirms a post go-live validation/smoke-test plan exists.
• Known Risks / Issues — Free text summary of any accepted risks or open issues.
• Evidence Repository Link — Link/path to the evidence pack (e.g. completed Word evidence form, test reports).
• Overall RAG Status — Red / Amber / Green — overall readiness for production approval.
• Approval Status — Pending / Approved / Approved with Conditions / Rejected.
• Approver Comments — Approver's notes, conditions, or reasons for rejection.
• Approval Date — Date the approval decision was recorded.

## Dashboard
Release Governance Dashboard
Auto-summarised from 'Release Tracker'
Overall RAG Status
Green | 1
Amber | 1
Red | 0
Approval Status
Pending | 1
Approved | 1
Approved with Conditions | 0
Rejected | 0
Total Releases Tracked
Releases with a Release ID | 2

## Release Tracker
Release Details | [7 empty] | Pipeline & Environment |  |  |  | Testing Evidence | [5 empty] | Readiness |  |  |  | Approval & Governance
Release ID | Application / Service | Release Version / Build | Change Request (CR) # | Release Type | Business Criticality | Release Manager | Lead Solution Architect (Approver) | Target Prod Deployment Date | Pipeline Build / Run # | Pre-Prod Deployment Date | Environment Parity Confirmed | Functional Testing Status | Functional Test Pass % | Security Scan Status | Security – Critical/High Open | Performance Test Status | UAT Sign-off Status | Rollback Plan Tested | Post-Deployment Validation Plan Ready | Known Risks / Issues | Evidence Repository Link | Overall RAG Status | Approval Status | Approver Comments | Approval Date
REL-2026-0417 | Payments Gateway | v3.4.1 | CR0089213 | Standard | High | A. Sharma | R. Whitfield | 2026-07-15 | Build #2451 | 2026-07-08 | Yes | Pass | 100 | Pass | 0 | Pass | Pass | Yes | Yes | None outstanding | \\evidence\REL-2026-0417\ | Green | Approved | All evidence verified; approved for go-live | 2026-07-10
REL-2026-0418 | Mobile Banking App | v9.2.0 | CR0089240 | Major | Critical | T. Nolan | R. Whitfield | 2026-07-20 | Build #2467 | 2026-07-12 | Partial | Conditional Pass | 92 | In Progress | 2 | Not Started | Pass | No | No | 2 High vulnerabilities being remediated; rollback test pending | \\evidence\REL-2026-0418\ | Amber | Pending | Awaiting security remediation and rollback test evidence